Hollingsworth Advisory Partners LLP

AMENDMENT A5 TO STATEMENT OF WORK

| Amendment reference | SOW-2025-022-A5 |
| --- | --- |
| Amends SOW | SOW-2025-022 |
| Client | Kesterly Logistics Group |
| Engagement | Payments Optimisation |
| Effective date | 25 January 2026 |

This amendment varies statement of work SOW-2025-022 with effect from 25 January 2026. All other terms of the original statement of work remain in full force. Where this amendment and the original conflict, this amendment prevails.

1.  Revised ceiling

|  | Original | Revised |
| --- | --- | --- |
| Ceiling hours | 2,660.00 | 3,404.80 |
| Ceiling amount (GBP) | 835,240.00 | 1,069,107.20 |
| Completion date | 25 December 2026 | 03 March 2027 |

Signed for and on behalf of the parties:

Hollingsworth Advisory Partners LLP  ..................................    Date  ............