Hollingsworth Advisory Partners LLP

AMENDMENT A2 TO STATEMENT OF WORK

| Amendment reference | SOW-2026-004-A2 |
| --- | --- |
| Amends SOW | SOW-2026-004 |
| Client | Westmoor Media Trust |
| Engagement | Inventory Programme |
| Effective date | 20 July 2026 |

This amendment varies statement of work SOW-2026-004 with effect from 20 July 2026. All other terms of the original statement of work remain in full force. Where this amendment and the original conflict, this amendment prevails.

1.  Revised ceiling

|  | Original | Revised |
| --- | --- | --- |
| Ceiling hours | 1,620.00 | 2,284.20 |
| Ceiling amount (GBP) | 489,240.00 | 689,828.40 |
| Completion date | 01 October 2026 | 26 December 2026 |

Signed for and on behalf of the parties:

Hollingsworth Advisory Partners LLP  ..................................    Date  ............